## Gantt chart
Mars Rover 2021
Group 18 |  | Project Start: | 2021-05-12
|  | Today: | 2021-06-16
|  | Display Week: | 1 |  |  | 2021-05-10 | [6 empty] | 2021-05-17 | [6 empty] | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14
[6 empty] | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Command
1: Research technologies | Xin Wang
1.1: Establish technology stack |  | 100% | 2021-05-12 | 2021-05-14 | 3
1.2: Initial design report |  | 100% | 2021-05-15 | 2021-05-15 | 1
2: Design basic wireframe | Xin Wang
2.1: Data flow analysis and component modelling |  | 100% | 2021-05-16 | 2021-05-16 | 1
3: Implement basic wireframe | Xin Wang
3.1: Establish basic website serving mechanism |  | 100% | 2021-05-16 | 2021-05-16 | 1
3.2: Website general layout design |  | 100% | 2021-05-17 | 2021-05-20 | 4
3.4: Websocket implementation |  | 100% | 2021-05-21 | 2021-05-23 | 3
3.5: Prettify layout |  | 100% | 2021-05-23 | 2021-05-25 | 3
4: Refactor and standardisation | Xin Wang
4.1: AWS deployment testing |  | 100% | 2021-05-26 | 2021-05-26 | 1
4.2: Cleaning up code |  | 100% | 2021-05-26 | 2021-05-26 | 1
4.4: Sensor display panel implementation |  | 100% | 2021-05-27 | 2021-05-28 | 1
4.5: State implementation for Canvas and Terminal |  | 100% | 2021-05-28 | 2021-06-01 | 5
4.6: Terminal implementation |  | 100% | 2021-06-01 | 2021-06-06 | 7
4.3: Database implementation |  | 100% | 2021-06-06 | 2021-06-08 | 3
5: Efficiency and security measures | Xin Wang
5.1: User authentication |  | 100% | 2021-06-09 | 2021-06-12 | 3
6: Improve frontend | Xin Wang | 100% | 2021-06-12 | 2021-06-13 | 1
Control
Research interface implementation | Igor Silin | 100% | 2021-05-12 | 2021-05-16
Implement WebSocket connection with Command | Igor Silin | 100% | 2021-05-16 | 2021-05-19
Plan UART connections with modules | Igor Silin | 100% | 2021-05-18 | 2021-05-23
Implement UART connection with Drive | Igor Silin | 100% | 2021-05-23 | 2021-05-27
Plan UART connection with Energy | Igor Silin | 100% | 2021-05-28 | 2021-05-31
Implement coordinate calculation algorithm | Igor Silin | 100% | 2021-06-01 | 2021-06-02
Establish JSON format transmission | Igor Silin | 100% | 2021-06-02 | 2021-06-02
Implement UART connection with Vision | Igor Silin | 100% | 2021-06-02 | 2021-06-10
Autonomous mode | Igor Silin | 100% | 2021-06-08 | 2021-06-13
Fine tune connection interfaces | Igor Silin | 100% | 2021-06-12 | 2021-06-15
Vision
Research | Ebby Samson | 100% | 2021-05-13 | 2021-05-16
Process pixels to detect balls | Ebby Samson | 100% | 2021-05-17 | 2021-05-21
Add filters to enable colour detection | Ebby Samson | 100% | 2021-05-24 | 2021-06-05
Accurately process ball data | Ebby Samson | 100% | 2021-05-25 | 2021-05-27
Implement automatic gain adjustment | Ebby Samson | 100% | 2021-05-26 | 2021-05-26
Clean up repository & fix bugs | Ebby Samson | 100% | 2021-05-31 | 2021-06-01
Add automatic saturation adjustment, improve gain adjustment | Ebby Samson | 100% | 2021-06-02 | 2021-06-02
Implement and test UART | Ebby Samson | 100% | 2021-06-02 | 2021-06-07
Add and test new filters | Ebby Samson | 100% | 2021-06-07 | 2021-06-08
Module Testing | Ebby Samson | 100% | 2021-06-07 | 2021-06-10
Drive
1.Research & Assemble the rover & Initial Testing | Aixin Zhang | 100% | 2021-05-13 | 2021-05-16 | 4
2. Implement Speed Control functionality & Testing | Aixin Zhang | bar: 2021-05-10 to 2021-06-13
2.1 Speed Control Code Writing |  | 100% | 2021-05-24 | 2021-05-26 | 3
2.2 Speed Control Testing with Position Control |  | 100% | 2021-05-27 | 2021-05-31 | 5
3. Implement Position Control functionality & Testing | Aixin Zhang | bar: 2021-05-10 to 2021-06-13
3.1 Split sections for better collaboration with control |  | 100% | 2021-05-16 | 2021-05-22 | 7
3.2 Design P controller algorithm & Testing |  | 100% | 2021-05-23 | 2021-05-24 | 2
3.3 Design I controller algorithm & Testing |  | 100% | 2021-05-25 | 2021-05-26 | 2
4. Implement Turning method & Testing | Aixin Zhang | bar: 2021-05-10 to 2021-06-13
4.1 Moving Forward, Backward & Turning Left, Right & Stop |  | 100% | 2021-05-16 | 2021-05-17 | 2
5. Implement measurement & Testing | Aixin Zhang | bar: 2021-05-10 to 2021-06-13
5.1 Check the efficiency for both wheels |  | 100% | 2021-05-18 | 2021-05-19 | 2
6. Input power consumption measurement | Aixin Zhang | 100% | 2021-05-20 | 2021-05-20 | 1
7. Finalising the Design with Integration & Control & Command | Aixin Zhang | bar: 2021-05-10 to 2021-06-13
7.1 Prepare some code for communicating with Control |  | 100% | 2021-06-01 | 2021-06-03 | 3
7.2 Prepare some testing code for Integration |  | 100% | 2021-06-04 | 2021-06-05 | 2
7.3 Write Command part code and test |  | 100% | 2021-06-04 | 2021-06-06 | 3
8.Improving the Design and Retesting | Aixin Zhang | bar: 2021-05-10 to 2021-06-13
8.1 Testing with Drive & Control & Command |  | 100% | 2021-06-07 | 2021-06-11 | 5
9. Finalising Report | Aixin Zhang | bar: 2021-05-10 to 2021-06-13
9.1 Bullet points and wrtie drive subsys report |  | 100% | 2021-06-05 | 2021-06-07 | 3
9.2 Intellectual Property Essay |  | 100% | 2021-06-08 | 2021-06-09 | 2
9.3 Statement |  | 100% | 2021-06-07 | 2021-06-07 | 1
9.4 Finalise and Compile |  | 100% | 2021-06-09 | 2021-06-13 | 1
Energy
Research | Kaling Ng | 100% | 2021-05-12 | 2021-05-16 | 5
First test on a single cell & Calculate the battery capacity | Kaling Ng | 100% | 2021-05-15 | 2021-05-18 | 4
Battery charging profile design | Kaling Ng | 100% | 2021-05-19 | 2021-05-25 | 7
Battery SoC estimation(Improve the state machine) | Kaling Ng | 100% | 2021-05-26 | 2021-05-28 | 3
Multiple-cell batteries(Parallel/Series) & Balancing | Kaling Ng | 100% | 2021-05-29 | 2021-06-03 | 6
Characterising PV panels& MPPT | Kaling Ng | 100% | 2021-06-01 | 2021-06-07 | 7
Battery SoH | Kaling Ng | 100% | 2021-06-08 | 2021-06-08 | 1
Communication with control and command | Kaling Ng | 100% | 2021-06-07 | 2021-06-08 | 2
Writing Report | Kaling Ng | 100% | 2021-06-06 | 2021-06-09 | 4
Finalising the code and testing | Kaling Ng | 100% | 2021-06-09 | 2021-06-12 | 4
Project demostration video | Kaling Ng | 100% | 2021-06-14 | 2021-06-15 | 2
Integration
Assemble Rover | Izzah Zafer | 100% | 2021-05-13 | 2021-05-14 | 2
Setup Testing Environment | Izzah Zafer | 100% | 2021-05-15 | 2021-05-15 | 1
Test for Vision | Izzah Zafer | 100% | 17/05/21 | 2021-06-07 | 22
Test for Drive | Izzah Zafer | 100% | 2021-05-18 | 2021-06-05 | 19
Test for Control <-> Drive | Izzah Zafer | 100% | 2021-05-25 | 2021-05-29 | 5
Test for Control <-> Vision | Izzah Zafer | 100% | 2021-06-06 | 2021-06-09 | 4
Test for Drive <-> Control <-> Command | Izzah Zafer | 100% | 2021-05-27 | 2021-05-28 | 2
Test for Drive <-> Control <-> Vision | Izzah Zafer | 100% | 2021-05-29 | 2021-06-14 | 17
Autonomous Mode Test | Izzah Zafer | 100% | 2021-06-11 | 2021-06-15 | 5
Setup Website and Server for Command Centre | Izzah Zafer | 100% | 2021-06-06 | 2021-06-06 | 1
Final Overall Test | Izzah Zafer | 100% | 2021-06-14 | 2021-06-15 | 2
Record Demo Video | Izzah Zafer | 100% | 2021-06-14 | 2021-06-15 | 2
Prepare Integration Section of Report | Izzah Zafer | 100% | 2021-06-03 | 2021-06-03 | 1
Prepare IP Essay | Izzah Zafer | 100% | 2021-06-08 | 2021-06-09 | 2
Note on G6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.